## Summary
Description | Feature Count
Denver Features proposed by Solution | 45
Team Capacity as per detailed planing | 38
Project plan available in Project Central link
https://app2.clarizen.com/Clarizen/Project/14730287041?viewid=351.33401537.24651457
Confluence Page for Feature Status & Assignment
https://confluence.nextgen.com/display/AI/5.9.6+%28Denver+Release%29+Interoperability

## Interop Capacity
| Per Resource Hours per Sprint | [5 empty] | Interop_Helios Hours per Sprint | [5 empty] | Interop_Sol Hours per Sprint
| Productive Hours | Features | PTR | Defect Backlog | Prod Support / Patch Work |  | Productive Hours | Features | PTR | Defect Backlog | Prod Support / Patch Work |  | Productive Hours | Features | PTR | Defect Backlog | Prod Support / Patch Work
Dev | 64 | 44 | 8 | 8 | 4 | Dev | 320 | 220 | 40 | 40 | 20 | Dev | 416 | 286 | 52 | 52 | 26
QA | 64 | 44 | 8 | 8 | 4 | QA | 320 | 220 | 40 | 40 | 20 | QA | 320 | 220 | 40 | 40 | 20
| Per Resource Hours per Block | [5 empty] | Interop_Helios Hours per Block | [5 empty] | Interop_Sol Hours per Block
| Productive Hours | Features | PTR | Defect Backlog | Prod Support / Patch Work |  | Productive Hours | Features | PTR | Defect Backlog | Prod Support / Patch Work |  | Productive Hours | Features | PTR | Defect Backlog | Prod Support / Patch Work
Dev | 192 | 132 | 24 | 24 | 12 | Dev | 960 | 660 | 120 | 120 | 60 | Dev | 1248 | 858 | 156 | 156 | 78
QA | 192 | 132 | 24 | 24 | 12 | QA | 960 | 660 | 120 | 120 | 60 | QA | 960 | 660 | 120 | 120 | 60
| Per Resource Hours per 2Block | [5 empty] | Interop_Helios Hours per 2 Block | [5 empty] | Interop_Sol Hours per 2 Block
| Productive Hours | Features | PTR | Defect Backlog | Prod Support / Patch Work |  | Productive Hours | Features | PTR | Defect Backlog | Prod Support / Patch Work |  | Productive Hours | Features | PTR | Defect Backlog | Prod Support / Patch Work
Dev | 384 | 264 | 48 | 48 | 24 | Dev | 1920 | 1320 | 240 | 240 | 120 | Dev | 2496 | 1716 | 312 | 312 | 156
QA | 384 | 264 | 48 | 48 | 24 | QA | 1920 | 1320 | 240 | 240 | 120 | QA | 1920 | 1320 | 240 | 240 | 120
| Per Resource Hours for Denver | [5 empty] | Interop_Helios Hours per Denver | [5 empty] | Interop_Sol Hours per Denver
| Productive Hours | Features | PTR | Defect Backlog | Prod Support / Patch Work |  | Productive Hours | Features | PTR | Defect Backlog | Prod Support / Patch Work |  | Productive Hours | Features | PTR | Defect Backlog | Prod Support / Patch Work
Dev | 1344 | 924 | 168 | 168 | 84 | Dev | 6720 | 4620 | 840 | 840 | 420 | Dev | 8736 | 6006 | 1092 | 1092 | 546
QA | 1344 | 924 | 168 | 168 | 84 | QA | 6720 | 4620 | 840 | 840 | 420 | QA | 6720 | 4620 | 840 | 840 | 420

## JIRA Dump
Issue Type | (Task Hours) | Issue key | Issue id | Summary | Status | Assignee | Reporter | Custom field (Epic Link) | Fix Version/s | Fix Version/s | Priority | Custom field (Severity) | Resolution | Custom field (Build Number) | Created | Updated | Due Date | Custom field (Potential Patient Safety Critical Issue) | Custom field (Regression Indicator) | Custom field (Found By Group) | Custom field (Known Issue Number) | Custom field (Rank) | Remaining Estimate | Î£ Remaining Estimate | Custom field (Feature Planned Estimate)
Epic |  | INTEROP-21812 | 910303 | Fortify Application Security scan issues | New |  | kaverianov |  | Interop Denver Release Spring 2022 |  | Standard Delivery |  |  |  | 2021-04-12 19:41 | 2021-04-12 19:45 |  | No |  |  |  | 2¦i10zi4:
Epic |  | INTEROP-21862 | 912252 | Interop - Rosetta DAL and Cache Optimizations | Construction - In Progress | team:sol | Cputtaswamy |  | Interop Denver Release Spring 2022 |  | Standard Delivery |  |  |  | 2021-04-15 06:30 | 2021-04-15 17:33 |  | No |  |  |  | 2¦i11c58:
Epic |  | INTEROP-20146 | 850456 | Interop Non Feature Defects | New |  | mkalola |  | Interop Denver Release Spring 2022 |  | Standard Delivery |  |  |  | 2021-01-06 20:16 | 2021-04-07 02:30 |  | No |  |  |  | 2¦i0qylb:
Epic |  | INTEROP-20362 | 855173 | NGE INTEROPERABILITY - QA - MISCELLANEOUS - DENVER | New | nbyri | nbyri |  | Interop Denver Release Spring 2022 |  | Standard Delivery |  |  |  | 2021-01-15 07:55 | 2021-03-22 13:19 | [5 empty] | 2¦i0rr2n:
Epic | 1000 | INTEROP-19938 | 841821 | TIOP056 - Rosetta - Enhance Tasking | New |  | hcarr |  | Interop Denver Release Spring 2022 |  | Standard Delivery |  |  |  | 2020-12-18 17:59 | 2021-02-17 14:04 |  | No |  |  |  | 2¦i0pndz:
Epic | 100 | INTEROP-19904 | 841804 | TIOP052 - Lockdown Rosetta interfaces | New | team:sol | hcarr |  | Denver Block 5-6 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2020-12-18 17:56 | 2021-04-20 21:05 |  | No |  |  |  | 2¦i0pn6f:
Epic | 2000 | INTEROP-19934 | 841767 | TIOP005 - Security Tags Receive (Â§ 170.315(b)(8) | New | team:sol | hcarr |  | Denver Block 5-6 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2020-12-18 17:58 | 2021-04-20 21:09 |  | No |  |  |  | 2¦i0pnd3:
Epic | 1000 | INTEROP-19935 | 841819 | TIOP006 - Security Tags Send (Â§ 170.315(b)(7) | New | team:sol | hcarr |  | Denver Block 5-6 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2020-12-18 17:58 | 2021-04-20 21:09 |  | No |  |  |  | 2¦i0pndb:
Epic | 200 | INTEROP-19907 | 841807 | TIOP053 - Support inbound ADT message for hospital admissionsÂ | New | hcarr | hcarr |  | Denver Block 5-6 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2020-12-18 17:56 | 2021-04-20 21:05 |  | No |  |  |  | 2¦i0pn73:
Epic | 500 | INTEROP-19915 | 841755 | TIOP024 - Immunizations: Support Reactions, Contraindication/Precaution and Special Indications - Export | New | team:sol | hcarr |  | Denver Block 5-6 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2020-12-18 17:57 | 2021-04-20 21:04 |  | No |  |  |  | 2¦i0pn8v:
Epic | 600 | INTEROP-19916 | 841756 | TIOP127 - Immunizations: Support Reactions, Contraindication/Precaution and Special Indications - Import | New | team:sol | hcarr |  | Denver Block 3-4 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2020-12-18 17:57 | 2021-04-20 21:10 |  | No |  |  |  | 2¦i0pn93:
Epic | 1000 | INTEROP-19941 | 841787 | TIOP166 - OPH - Import discrete data (Visual Acuity) data from CCDA | New | team:sol | hcarr |  | Denver Block 5-6 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2020-12-18 19:10 | 2021-04-20 21:18 |  | No |  |  |  | 2¦i0pnnj:
Epic | 200 | INTEROP-19931 | 841765 | TIOP224 - Update LabCorp 2D Barcode, Requisition, and Result reports to match latest standard | New | team:helios | hcarr |  | Denver Block 5-6 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2020-12-18 17:58 | 2021-04-20 21:07 |  | No |  |  |  | 2¦i0pncf:
Epic | 400 | INTEROP-19913 | 841811 | TIOP051 - Laboratory Export â€“ support HL7 v2.5.1 (COVID-19 focus) | New | team:sol | hcarr |  | Denver Block 5-6 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2020-12-18 17:57 | 2021-04-20 21:04 |  | No |  |  |  | 2¦i0pn8f:
Epic | 600 | INTEROP-19914 | 841754 | TIOP100 - Note Functionality in Rosetta Holding Tank (Idea-8183) | New | team:sol | hcarr |  | Denver Block 3-4 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2020-12-18 17:57 | 2021-04-20 20:59 |  | No |  |  |  | 2¦i0pn8n:
Epic |  | INTEROP-21889 | 914065 | TIOP255 - Interop shall support EHR document content in C-CDA as clinical notes | New |  | hcarr |  | Denver Block 3-4 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2021-04-19 16:40 | 2021-04-20 21:17 |  | No |  |  |  | 2¦i11n10:
Epic |  | INTEROP-21890 | 914136 | TIOP256 - Interop Rules Engine shall support the ability to bypass PAQ for HL7 documents | New |  | hcarr |  | Denver Block 3-4 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2021-04-19 16:46 | 2021-04-20 21:17 |  | No |  |  |  | 2¦i11n18:
Epic | 360 | INTEROP-20294 | 854643 | TIOP097 - Clinical Message Manager â€“ Allow Creation of Patient using Demographics in HL7 or C-CDA Documents (Idea-9003) | New | team:helios | tlipcsey |  | Denver Block 5-6 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2021-01-13 19:40 | 2021-04-20 21:03 |  | No |  |  |  | 2¦i0rmzj:
Epic |  | INTEROP-21303 | 899153 | TIOP253 - INTEROP shall support procedures with more than 12 diagnosis codes | Feature Refinement In Progress | team:sol | hcarr |  | Denver Block 3-4 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2021-03-30 17:03 | 2021-04-20 21:19 |  | No |  |  |  | 2¦i0z42k:
Epic | 1000 | INTEROP-20298 | 854474 | TIOP165 - Large CCDAs causing performance issues in the CCDA viewer and on import | Construction - In Progress | team:helios | hcarr |  | Denver Block 3-4 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2021-01-13 19:42 | 2021-04-16 07:27 |  | No |  |  |  | 2¦i0rn0f:
Epic | 135 | INTEROP-20295 | 854644 | TIOP092 - Maintain Window Size of Clinical Reconciliation Module (Idea-8664) | New | team:helios | hcarr |  | Denver Block 5-6 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2021-01-13 19:40 | 2021-04-20 21:06 |  | No |  |  |  | 2¦i0rmzr:
Epic |  | INTEROP-21651 | 904339 | TIOP254 - INTEROP shall support the ability to place equipment reports into categories | New | team:helios | hcarr |  | Denver Block 3-4 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2021-04-06 22:17 | 2021-04-07 20:40 |  | No |  |  |  | 2¦i0zzd8:
Epic | 600 | INTEROP-19933 | 841818 | TIOP134 - Support automated query of immunization history and forecast from Imm Registr | New | team:sol | hcarr |  | Denver Block 3-4 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2020-12-18 17:58 | 2021-04-20 21:00 |  | No |  |  |  | 2¦i0pncv:
Epic | 600 | INTEROP-19937 | 841768 | TIOP225 - Consent Improvements for Immunizations (COVID focus) | Feature Readiness Validation | team:sol | hcarr |  | Denver Block 3-4 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2020-12-18 17:59 | 2021-04-20 15:30 |  | No |  |  |  | 2¦i0pndr:
Epic |  | INTEROP-21650 | 904320 | TIOP129 - Custom View: Support Import of Lab Results from CCDA | New | team:helios | hcarr |  | Denver Block 3-4 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2021-04-06 22:01 | 2021-04-07 00:10 |  | No |  |  |  | 2¦i0zzd0:
Epic | 400 | INTEROP-19909 | 841808 | TIOP181 - Ability to search and/or filter on Agents names on the Agent list in the RMC | New | team:helios | hcarr |  | Denver Block 3-4 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2020-12-18 17:56 | 2021-04-20 21:00 |  | No |  |  |  | 2¦i0pn7j:
Epic | 800 | INTEROP-19917 | 841757 | TIOP116 - The system shall support sending information about all external interface transactions of Rosetta and HIE Gateway | New | team:sol | hcarr |  | Denver Block 3-4 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2020-12-18 17:57 | 2021-04-20 20:59 |  | No |  |  |  | 2¦i0pn9b:
Epic | 1000 | INTEROP-19920 | 841759 | TIOP186 - Custom Viewer - support additional sections | Feature Refinement Done | team:sol | hcarr |  | Denver Block 1-2 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2020-12-18 17:57 | 2021-04-13 19:18 |  | No |  |  |  | 2¦i0pn9z:
Epic | 1000 | INTEROP-19924 | 841814 | TIOP149 - Support Midmark 8x in the new Equipment Module | New | team:helios | hcarr |  | Denver Block 5-6 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2020-12-18 17:58 | 2021-04-20 21:09 |  | No |  |  |  | 2¦i0pnav:
Epic | 400 | INTEROP-19921 | 841813 | TIOP189 - Ability to launch the external application module from the top toolbar and/or the menu bar in PM | Feature Refinement In Progress | team:helios | hcarr |  | Denver Block 3-4 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2020-12-18 17:57 | 2021-04-20 21:20 |  | No |  |  |  | 2¦i0pna7:
Epic |  | INTEROP-20692 | 867726 | TIOP243 - Improve logic for provenance capture when data is committed to the database via CMM | Construction - In Progress | team:sol | hcarr |  | Denver Block 1-2 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2021-02-08 17:11 | 2021-04-15 07:32 |  | No |  |  |  | 2¦i0ttn3:
Epic | 400 | INTEROP-20297 | 854473 | TIOP072 - Interop rules engine -Â Add the ability to suspend the use of a rule | Feature Refinement Done | team:sol | hcarr |  | Denver Block 1-2 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2021-01-13 19:42 | 2021-04-20 04:11 |  | No |  |  |  | 2¦i0rn07:
Epic |  | INTEROP-20544 | 863441 | TIOP234 - eCR Enhancements to support a more thorough history of changes to Custom Trigger Codes | Feature Refinement Done | team:sol | hcarr |  | Denver Block 3-4 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2021-01-29 17:01 | 2021-04-20 21:01 |  | No |  |  |  | 2¦i0t3k7:
Epic |  | INTEROP-20761 | 871901 | TIOP246 - New Patient Summary feature in NGE shall support existing Interoperability Features | Feature Refinement In Progress |  | hcarr |  | Denver Block 3-4 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2021-02-16 19:42 | 2021-04-06 23:21 |  | No |  |  |  | 2¦i0uiv3:
Epic | 600 | INTEROP-19922 | 841760 | TIOP216 - Electronic case reporting(eCR) enhancements | Feature Refinement In Progress | team:helios | hcarr |  | Denver Block 3-4 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2020-12-18 17:57 | 2021-04-11 17:18 |  | No |  |  |  | 2¦i0pnaf:
Epic |  | INTEROP-20714 | 868609 | TIOP237 - Ability to right click on an HIE Document and create/match an encounter | Feature Refinement In Progress | team:sol | hcarr |  | Denver Block 3-4 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2021-02-09 22:50 | 2021-04-06 23:22 |  | No |  |  |  | 2¦i0tyq7:
Epic |  | INTEROP-20545 | 863442 | TIOP233 - Electronic case reporting(eCR) - RCTC enhancements | Feature Refinement In Progress | team:helios | hcarr |  | Denver Block 3-4 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2021-01-29 17:02 | 2021-04-06 23:23 |  | No |  |  |  | 2¦i0t3kf:
Epic |  | INTEROP-20713 | 868522 | TIOP236 - Interop Rules Engine - Ability to create encounter for HIE Documents Received | Feature Refinement In Progress | team:sol | hcarr |  | Denver Block 3-4 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2021-02-09 22:50 | 2021-04-14 14:09 |  | No |  |  |  | 2¦i0typz:
Epic | 1000 | INTEROP-19905 | 841805 | TIOP044 - 360x Project | Feature Refinement In Progress | team:sol | hcarr |  | Denver Block 5-6 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2020-12-18 17:56 | 2021-04-20 21:10 |  | No |  |  |  | 2¦i0pn6n:
Epic |  | INTEROP-21274 | 898932 | TIOP076 Custom rules engine - Max/Min screen | Feature Refinement Done | team:sol | hcarr |  | Denver Block 3-4 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2021-03-30 12:22 | 2021-04-20 14:13 |  | No |  |  |  | 2¦i0z2qc:
Epic | 300 | INTEROP-20296 | 854472 | TIOP160 - Medical Summary Utility sends a C-CDA with "Normal Sharing" code when choosing Confidentiality Code of "Restricted Sharing" | Feature Refinement Done | team:sol | hcarr |  | Denver Block 1-2 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2021-01-13 19:40 | 2021-04-06 22:46 |  | No |  |  |  | 2¦i0rmzz:
Epic | 200 | INTEROP-19939 | 841769 | TIOP184 - Enhance HIE Consent Effective Date | Feature Refinement Done | team:sol | hcarr |  | Denver Block 1-2 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2020-12-18 17:59 | 2021-04-20 09:55 |  | No |  |  |  | 2¦i0pne7:
Epic | 400 | INTEROP-19918 | 841758 | TIOP183 - Record Rosetta information; i.e. version, server name, etc | Feature Refinement Done | team:sol | hcarr |  | Denver Block 1-2 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2020-12-18 17:57 | 2021-04-07 07:50 |  | No |  |  |  | 2¦i0pn9j:
Epic | 410 | INTEROP-4663 | 434426 | [TIOP--125]: Support Display of search history and export History in Data Share Module | Feature Refinement Done | team:helios | hcarr |  | Denver Block 1-2 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2019-04-25 18:31 | 2021-04-06 23:31 | [5 empty] | 2¦hywrof:
Epic | 198 | INTEROP-4802 | 435257 | [TIOP:124] Interoperability (Data Share) Module to be hosted from within EHR - Support launch of Data Share Module w/o Share or Carequality | Feature Refinement Done | team:helios | hcarr |  | Denver Block 3-4 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2019-04-26 16:47 | 2021-04-14 16:24 | [5 empty] | 2¦hywx1r:
Epic | 510 | INTEROP-4624 | 434387 | [TIOP123]: Interoperability (Data Share) Module - Support MSU options | Feature Refinement Done | team:helios | hcarr |  | Denver Block 1-2 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2019-04-25 18:31 | 2021-04-16 05:14 | [5 empty] | 2¦hywrgn:
Epic | 1189 | INTEROP-4702 | 435157 | Interoperability (Data Share) Module to be hosted from within EHR - Support MSU Import functionality | Feature Refinement Done | team:helios | hcarr |  | Denver Block 1-2 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2019-04-26 16:47 | 2021-04-06 23:38 | [5 empty] | 2¦hywwiv:
Epic |  | INTEROP-4553 | 434316 | TIOP115 DSM - include the Export functionality from the MSU. | Feature Refinement Done | team:helios | hcarr |  | Denver Block 1-2 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2019-04-25 18:23 | 2021-04-06 23:39 | [5 empty] | 2¦hywr2f:
Epic | 96 | INTEROP-20392 | 858252 | TIOP229 - Backport VDP - Expanded sign-off functionality for Legal Authenticator | Construction - In Progress | team:sol | Cputtaswamy |  | Denver Block 1-2 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2021-01-21 04:20 | 2021-04-06 23:28 |  | No |  |  |  | 2¦i0s9cn:
Epic | 102 | INTEROP-20399 | 858267 | TIOP228 - VDP - Expanded sign-off functionality for Legal Authenticator | Construction - In Progress | team:sol | Cputtaswamy |  | Denver Block 1-2 | Interop Denver Release Spring 2022 | Standard Delivery |  |  |  | 2021-01-21 04:59 | 2021-04-20 03:50 |  | No |  |  |  | 2¦i0s9hj:

## Denver Interop Work Plan
Block 1&2 |  |  |  | Block 3&4 |  |  |  | Block 5&6 |  |  |  | Block 7
Interop _ Helios | Dev | QA | UA | Interop _ Helios | Dev | QA | UA | Interop _ Helios | Dev | QA | UA | Interop _ Helios | Dev | QA | UA
TIOP115 | 330 | 550 | 24 | TIOP115 | 600 | 300 |  | TIOP189 | 400 | 100 | 14 | TIOP255 | 800 | 250
TIOP122 | 1189 | 250 | 25 | TIOP122 | 368 | 520 |  | TIOP092 | 135 | 35 | 5 | TIOP254
TIOP123 | 96 | 300 | 8 | TIOP123 | 100 | 50 |  | TIOP233 | 200 | 100 | 13 | TIOP224 | 200 | 100 | 7
TIOP125 | 410 | 120 | 8 | TIOP125 | 120 | 134 |  | TIOP234 | 150 | 100 | 14 | TIOP216 | 600 | 250 | 7
|  |  |  | TIOP100 | 600 | 250 | 14 | TIOP165 | 0 | 130 | 14
|  |  |  | TIOP181 | 400 | 100 | 14 | TIOP097 | 360 | 180 | 9
|  |  |  | TIOP124 | 198 | 110 | 5 | TIOP254 |  |  | 14
[8 empty] | TIOP255 | 200 | 500 | 14
Total Estimate | 2025 | 1220 | 65 | Total Estimate | 2386 | 1464 | 33 | Total Estimate | 1445 | 1145 | 97 | Total Estimate | 1600 | 600 | 7
Feature Capacity | 1320 | 1320 |  | Feature Capacity | 1320 | 1320 |  | Feature Capacity | 1320 | 1320 |  | Feature Capacity | 960 | 960
Interop_Sol | Dev | QA | UA | Interop_Sol | Dev | QA | UA | Interop_Sol | Dev | QA | UA | Interop_Sol | Dev | QA | UA
TIOP072 | 400 | 100 | 0 | TIOP076 | 100 | 50 | 5 | TIOP052 | 200 | 200 | 14 | TIOP-166 | 1000
TIOP160 | 300 | 60 | 5 | TIOP116 | 800 | 400 | 14 | TIOP236 | 350 | 150 | 14 | TIOP-134 | 600 | 300
TIOP183 | 230 | 50 | 14 | TIOP225 | 300 | 180 | 14 | TIOP237 | 450 | 120 | 14 | TIOP256
TIOP184 | 200 | 100 | 6 | TIOP253 | 200 | 150 | 14 | TIOP044 | 200 | 350 | 5
TIOP243 | 257 | 194 | 40 | TIOP186 | 800 | 600 |  | TIOP051 | 200 | 100 | 14
TIOP186 | 200 | 120 | 0 |  |  |  |  | TIOP246 | 100 | 60 | 7
TIOP228 | 158 | 40 | 5 |  |  |  |  | TIOP256 | 1000
TIOP229 | 16 | 8 | 3
Total Estimate | 1761 | 672 | 73 | Total Estimate | 2200 | 1380 | 47 | Total Estimate | 2500 | 980 | 68 | Total Estimate | 1600 | 300 | 0
Feature Capacity | 1716 | 1320 |  | Feature Capacity | 1716 | 1320 |  | Feature Capacity | 1716 | 1320 |  | Feature Capacity | 1248 | 960

## Block 1-2
Block 1&2 - ( 4/14-5/25, 5/26-7/6)
Interop _ Helios | Dev | QA | UA
TIOP115 | 330 | 550 | 24
TIOP122 | 1189 | 250 | 25
TIOP123 | 510 | 300 | 8
TIOP125 | 410 | 120 | 8
Total Estimate | 2439 | 1220 | 65
Feature Capacity | 1320 | 1320
Interop_Sol | Dev | QA | UA
TIOP072 | 400 | 100 | 0
TIOP160 | 300 | 60 | 5
TIOP183 | 230 | 50 | 14
TIOP184 | 200 | 100 | 6
TIOP243 | 257 | 194 | 40
TIOP186 | 1000 | 720 | 0
TIOP228 | 158 | 40 | 5
TIOP229 | 16 | 8 | 3
Total Estimate | 2561 | 1272 | 73
Feature Capacity | 1716 | 1320

## Block 3-4
Block 3&4 - (7/14-8/24,8/24-10/5)
Interop _ Helios | Dev | QA | UA
TIOP115 |  | 300
TIOP122 | 368 | 520
TIOP123 | 125 | 50
TIOP125 | 0 | 134
TIOP100 | 600 | 250 | 14
TIOP181 | 400 | 100 | 14
TIOP124 | 198 | 110 | 5
Total Estimate | 1691 | 1464 | 33
Feature Capacity | 1320 | 1320
Interop_Sol | Dev | QA | UA
TIOP076 | 100 | 50 | 5
TIOP116 | 800 | 500 | 14
TIOP225 | 300 | 200 | 14
TIOP253 | 250 | 200 | 14
TIOP256
Total Estimate | 1450 | 950 | 47
Feature Capacity | 1716 | 1320

## Block 5-6
Block 5&6 - (10/13-11/23, 11/24-1/4)
Interop _ Helios | Dev | QA | UA
TIOP189 | 400 | 100 | 14
TIOP092 | 135 | 35 | 5
TIOP233 |  | 100 | 13
TIOP234 | 200 | 100 | 14
TIOP165 | 0 | 130 | 14
TIOP097 | 360 | 180 | 9
TIOP254 |  |  | 14
TIOP255 | 1000 | 500 | 14
Total Estimate | 2095 | 1145 | 65
Feature Capacity | 1320 | 1320
Interop_Sol | Dev | QA | UA
TIOP052 | 600 | 350 | 14
TIOP236 | 180 | 120 | 14
TIOP237 | 400 | 250 | 14
TIOP044 | 200 | 350 | 5
TIOP051 | 300 | 150 | 14
TIOP246 | 0 | 60 | 7
TIOP237
Total Estimate | 1680 | 1280 | 68
Feature Capacity | 1716 | 1320

## Block 7
Block 7 (1/12-2/22)
Interop _ Helios | Dev | QA | UA
TIOP255 | 800 | 250
TIOP254
TIOP224 | 200 | 100
TIOP216 | 600 | 250 | 7
Total Estimate | 1600 | 600 | 7
Feature Capacity
Interop_Sol | Dev | QA | UA
TIOP-166 | 1000
TIOP-134 | 600 | 300
TIOP256
Total Estimate | 1600 | 300 | 0
Feature Capacity
overlaps with regression testing starting 2/9 -3/8/22
Pulse | Dev | QA | UA
ACE-275 | 40 | 40 | 20
ACE-316 | 60 | 50 | 25
ACE-280 | 70 | 50 | 25
ACE-333 | 60 | 60 | 25
Total Estimate | 230 | 200 | 95
Feature Capacity | 370 | 360