## Sheet1
Feature | JIRA ID | Work Items | Status | Dev ETA | QA ETA | Comments
TIOP-122 | https://jira.nextgen.com/browse/INTEROP-4702 | https://jira.nextgen.com/browse/INTEROP-4708 | QA in Progress |  | 2021-09-07
|  | https://jira.nextgen.com/browse/INTEROP-4712 | Construction In Progress |  | 2021-10-05
|  | https://jira.nextgen.com/browse/INTEROP-4707 | Construction Complete |  | 2021-09-17
|  | https://jira.nextgen.com/browse/INTEROP-4710 | Construction In Progress |  | 2021-10-05
|  | https://jira.nextgen.com/browse/INTEROP-4711 | Refinement done |  | 2021-10-05
|  | https://jira.nextgen.com/browse/INTEROP-23897 | QA in Progress |  | 2021-09-01
TIOP-123 | https://jira.nextgen.com/browse/INTEROP-4624 | https://jira.nextgen.com/browse/INTEROP-21291 | QA in Progress |  | 2021-09-01
TIOP-124 | https://jira.nextgen.com/browse/INTEROP-4802 | https://jira.nextgen.com/browse/INTEROP-4807 | QA in Progress |  | 2021-09-23
|  | https://jira.nextgen.com/browse/INTEROP-23489 | QA in Progress |  | 2021-09-24
|  | https://jira.nextgen.com/browse/INTEROP-23490 | QA in Progress |  | 2021-09-25
|  | https://jira.nextgen.com/browse/INTEROP-23491 | QA in Progress |  | 2021-09-07
|  | https://jira.nextgen.com/browse/INTEROP-23492 | QA in Progress |  | 2021-09-08
|  | https://jira.nextgen.com/browse/INTEROP-23559 | Refinement Done |  | 2021-09-30
|  | https://jira.nextgen.com/browse/INTEROP-23560 | Refinement Done |  | 2021-09-30
TIOP-125 | https://jira.nextgen.com/browse/INTEROP-4663 | https://jira.nextgen.com/browse/INTEROP-4558 | Construction In Progress |  | 2021-10-30
|  | https://jira.nextgen.com/browse/INTEROP-4665 | Construction In Progress |  | 2021-10-30
TIOP-115 | https://jira.nextgen.com/browse/INTEROP-4553 | https://jira.nextgen.com/browse/INTEROP-21188 | Construction In Progress |  | 2021-10-30
|  | https://jira.nextgen.com/browse/INTEROP-21292 | Construction Complete |  |  | QA effort was Not considered previously, since it was only Dev effort required and no QA. We still have some clarifications pending. Will update QA ETA once we get the complete information.
|  | https://jira.nextgen.com/browse/INTEROP-4559 | QA in Progress |  | 2021-09-10
|  | https://jira.nextgen.com/browse/INTEROP-21186 | Construction In Progress
|  | https://jira.nextgen.com/browse/INTEROP-21187 | QA in Progress |  | 2021-09-07
TIOP-165 | https://jira.nextgen.com/browse/INTEROP-20298 | https://jira.nextgen.com/browse/INTEROP-21750 | Construction Complete |  | 2021-10-30
|  | https://jira.nextgen.com/browse/INTEROP-21731 | Construction Complete |  | 2021-10-31